| **District/Campus** | **Fiscal Year:** | | | |
| --- | --- | --- | --- | --- |
| **SMART Goal 1** By 2021 \_\_\_\_ISD will have fully developed curriculum, classroom, a job placement program designed for all students who wish to enroll in an Internship program for one or two semester(s) their senior year. | | | | |
| **Intended Outcomes:**   1. By school year 2018-2019 a full curriculum will be developed for an Internship program. 2. By school year 2019-2020 requirements for student enrollment in the Internship program will be identified and approved and a teacher/project manager job description will be created 3. By school year 2019-2020 the district will have worked with business and community partners within the county to develop a Student Internship Memorandum of Understanding between both parties (ISD and Partner) and train Partners on the aspects of the curriculum and learning outcomes for students. 4. By school year 2020-2021 10% of the senior class will be enrolled in a Student Internship class. | | | | |
| **YEAR ONE**  **Activities to Be Carried Out to Accomplish Goal** | **Persons or Positions Responsible** | **Timeline** | **Resource Needs** | **Completion Date** |
| 1. A district committee will be formed to research current internship programs and curriculum in the state of Texas | Assistant Principal  Business/Community Representative  District C&I Director | Sept. 1 – Nov 25, 2018 | Calendared meeting dates and meeting room  Research tools and materials  Strategic planned |  |
| 1. Write a curriculum with pacing guide for a one and two semester Student Internship course and corresponding Syllabus, including student requirements | C&I Director  CTE Teacher Rep  Core Teacher Rep | Jan 5, 2019-June 30, 2019 | Research materials  Sample curriculum from other districts  Calendared work meetings |  |
| 1. Write a MOU between ISD and business/community partner for Student Internship Program | Asst. Supt  C&I Director  Business/Community  Partners | Jan 5, 2019 – July 1, 2019 | Calendared meetings and online work space such as Google Docs or Google Hangout |  |